## Roadmap
AquaLog Roadmap
Now / Next / Later • Updated February 2026
NOW | NEXT | LATER
Weekend 1–2 | v1.1 (March–April) | v2.0+
Log Button | Customizable Goal | Apple Watch
Prominent tap target to log one glass of water | Let users set a personal daily target (stepper) | Complication + quick-log from the wrist
Ring Chart | History View | HealthKit Sync
Animated circular progress showing glasses / 8 | Simple list or chart of the past 7–30 days | Write water intake to Apple Health
Glass Counter | Undo Last Log | Home Screen Widget
Numeric "X / 8 glasses" label | Shake-to-undo or button to remove accidental tap | Glanceable ring chart via WidgetKit
SwiftData Model | Goal Animation | Reminders
Persist each log entry with timestamp | Confetti or glow when daily target is reached | Scheduled push notifications to drink water
Daily Reset | Haptic Feedback | iPad Layout
Show only today's entries based on device calendar | Subtle tap on each log action | Adaptive layout for larger screens
Single-Screen UI
SwiftUI layout: ring + count + button
Capacity: Solo developer, 2 weekends (~20–24 hrs) for MVP. Now = committed scope. Next/Later = prioritized backlog.

## Detail
AquaLog — Detailed Roadmap
Item | Description | Priority | Effort | Dependencies
NOW — MVP (Weekend 1–2)
Log Button | Tap to increment daily glass count by 1 | P0 | 2 hrs | None
Ring Chart | Animated circular progress (0–8 fill) | P0 | 4 hrs | None
Glass Counter | Numeric X/8 label, real-time update | P0 | 1 hr | Log Button
SwiftData Model | WaterLog entity with timestamp field | P0 | 2 hrs | None
Daily Reset | Filter query by device calendar day | P0 | 1 hr | SwiftData Model
Single-Screen UI | Compose ring + count + button in SwiftUI | P0 | 3 hrs | All above
NEXT — v1.1 Fast Follow
Customizable Goal | Settings sheet with stepper (1–20 glasses) | P1 | 3 hrs | SwiftData Model
History View | List/bar chart of past 7–30 days | P1 | 5 hrs | SwiftData Model
Undo Last Log | Remove most recent entry (shake or button) | P1 | 2 hrs | Log Button
Goal Animation | Confetti/glow on reaching daily target | P1 | 2 hrs | Ring Chart
Haptic Feedback | UIImpactFeedbackGenerator on each tap | P1 | 0.5 hr | Log Button
LATER — v2.0+
Apple Watch | Complication + quick-log from wrist | P2 | 12 hrs | SwiftData Model
HealthKit Sync | Write HKQuantityType.dietaryWater | P2 | 4 hrs | SwiftData Model
Home Screen Widget | WidgetKit ring chart (small + medium) | P2 | 6 hrs | Ring Chart
Reminders | UNUserNotificationCenter scheduled nudges | P2 | 3 hrs | None
iPad Layout | Adaptive layout for larger screens | P2 | 4 hrs | Single-Screen UI
MVP Total Estimate |  | P0 | ~13 hrs